**June Accomplishments:**

-Overall Construction 27% complete  
-Auxiliary transformer is on site  
-All pedestals complete  
-Tanks currently under construction  
-Turbine and generator scheduled to be delivered in August  
-Foundations 80% complete  
- Power Distribution Center complete